## Guide and Instructions
Countermeasure Guide and Instructions
Purpose
This template will allow you to list your root causes and develop countermeasures/ propose solutions to counteract the root cause impacts to your process.
Instructions
1 | Take the problem statement from your charter and populate the problem statement field.
2 | Carry over your root causes from your 5 Why exercise to this template.
3 | Brainstorm with your team, countermeasures for each root cause. You may have more than one countermeasure for a root cause, so list and score them separately in the grid.
4 | Score the countermeasures using the drop down scoring under each criteria; Feasibility, Effort, Impact and Cost. NOTE - The scoring levels for each criteria to ensure you score appropriately. | List all the suppliers to this process. | List all the suppliers to this process. | List all the suppliers to this process. | List all the suppliers to this process. | List all the suppliers to this process. | List all the suppliers to this process. | List all the suppliers to this process. | List all the suppliers to this process. | List all the suppliers to this process. | List all the suppliers to this process. | List all the suppliers to this process.
5 | The total score will be automatically calculated. | List all the inputs that are required for the process. | List all the inputs that are required for the process. | List all the inputs that are required for the process. | List all the inputs that are required for the process. | List all the inputs that are required for the process. | List all the inputs that are required for the process. | List all the inputs that are required for the process. | List all the inputs that are required for the process. | List all the inputs that are required for the process. | List all the inputs that are required for the process. | List all the inputs that are required for the process.
6 | Decide with your team which countermeasures / actions will be implemented. | List the outputs from the process. | List the outputs from the process. | List the outputs from the process. | List the outputs from the process. | List the outputs from the process. | List the outputs from the process. | List the outputs from the process. | List the outputs from the process. | List the outputs from the process. | List the outputs from the process. | List the outputs from the process.
7 | Assign an owner(s) to each action that will be implemented, decide on the due date to be completed. | List the customers of the process. | List the customers of the process. | List the customers of the process. | List the customers of the process. | List the customers of the process. | List the customers of the process. | List the customers of the process. | List the customers of the process. | List the customers of the process. | List the customers of the process. | List the customers of the process.
8 | Track the implementation of the action items. Baseline your improvement (Improve Phase)

## Countermeasure Template
Problem Statement
Number | Root Cause (From Fishbone/ 5 Why) | Countermeasure / Proposed Solution (What) | Feasibility | Specific Actions (How will this countermeasure be implemented) | Effort (1=High Effort, 10= Low Effort) | Impact (1=Low Impact, 10=High Impact) | Cost (1=High Cost, 10= Low Cost) | Overall Score | Go/ No Go | Owner (Who is the lead on this) | Due Date | Scoring | Go/ No Go
1 | [7 empty] | 0 |  |  |  | 1 | Yes
2 | [7 empty] | 0 |  |  |  | 3 | No
3 | [7 empty] | 0 |  |  |  | 5
4 | [7 empty] | 0 |  |  |  | 7
5 | [7 empty] | 0 |  |  |  | 10
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0
26 | [7 empty] | 0
27 | [7 empty] | 0
28 | [7 empty] | 0
29 | [7 empty] | 0
30 | [7 empty] | 0
31 | [7 empty] | 0
32 | [7 empty] | 0
33 | [7 empty] | 0
34 | [7 empty] | 0
35 | [7 empty] | 0
36 | [7 empty] | 0
37 | [7 empty] | 0
38 | [7 empty] | 0
39 | [7 empty] | 0
40 | [7 empty] | 0
41 | [7 empty] | 0
42 | [7 empty] | 0
43 | [7 empty] | 0
44 | [7 empty] | 0
45 | [7 empty] | 0
46 | [7 empty] | 0
47 | [7 empty] | 0
48 | [7 empty] | 0
49 | [7 empty] | 0
50 | [7 empty] | 0
51 | [7 empty] | 0
52 | [7 empty] | 0
53 | [7 empty] | 0
54 | [7 empty] | 0
55 | [7 empty] | 0
56 | [7 empty] | 0
57 | [7 empty] | 0
58 | [7 empty] | 0
59 | [7 empty] | 0
60 | [7 empty] | 0
61 | [7 empty] | 0
62 | [7 empty] | 0
63 | [7 empty] | 0
64 | [7 empty] | 0
65 | [7 empty] | 0
66 | [7 empty] | 0
67 | [7 empty] | 0
68 | [7 empty] | 0
69 | [7 empty] | 0
70 | [7 empty] | 0
71 | [7 empty] | 0
72 | [7 empty] | 0
73 | [7 empty] | 0
74 | [7 empty] | 0
75 | [7 empty] | 0
Note on C4: Problem statement from the charter.
Note on E5: 1 = Low Feasibility of implementation 5 = Medium 10 = High Feasibility
Note on G5: 1=High Effort 5= Medium Effort 10= Low Effort
Note on H5: 1=Low impact 5= Medium Impact 10= High Impact This criteria is weighted by 2
Note on I5: 1=High Cost 5= Medium Cost 10= Low Cost
Note on K5: Choose whether this action will be implemented.

## Countermeasure Example
| Problem Statement | Audit Evidence is late from the client, lateness averages 5 days after due date.
Number | Root Cause (From Fishbone/ 5 Why) | Countermeasure / Proposed Solution (What) | Feasibility | Specific Actions (How will this countermeasure be implemented) | Effort (1=High Effort, 10= Low Effort) | Impact (1=Low Impact, 10=High Impact) | Cost (1=High Cost, 10= Low Cost) | Overall Score | Go/ No Go | Owner (Who is the lead on this) | Due Date | Scoring | Go/ No Go
1 | Client is busy with month end, forget to turn in evidence. | Monthly close checklist | 5 | Add our evidence in with client monthly close checklist. Make it a part of their close. | 7 | 7 | 10 | 36 | Yes | Jon | 2024-04-01 | 1 | Yes
2 | We are using different naming convention than what the client uses. | Change Names of Evidence | 10 | Change naming of evidence, use the naming convention the client is used to. | 10 | 5 | 10 | 40 | Yes | Bert | 2024-04-01 | 3 | No
3 |  | Train client | 3 | Train up the client on our naming convention. | 3 | 1 | 10 | 18 | No |  |  | 5
4 | No escalation plan in place | Escalation plan | 10 | Develop escalation plan with the client, get agreement and communicate to all parties involved. | 10 | 7 | 10 | 44 | Yes | Karen | 2024-03-30 | 7
5 |  | Reward system | 10 | Develop reward/ recognition for client areas that turn in evidence consistently on time. Give out at the end of the year. | 10 | 5 | 5 | 35 | Yes | Karen | 2024-03-30 | 10
6 | Client is unaware of some of the due dates | Kickoff meeting | 10 | Have a kickoff meeting with client that includes reviewing the evidence list and due dates. | 10 | 7 | 10 | 44 | Yes | Phillip | 2024-02-28
7 |  | Weekly status meetings | 10 | Start weekly status meetings with client covering the status of evidence turn in. | 10 | 10 | 10 | 50 | Yes | Phillip | 2024-02-28
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0
26 | [7 empty] | 0
27 | [7 empty] | 0
28 | [7 empty] | 0
29 | [7 empty] | 0
30 | [7 empty] | 0
31 | [7 empty] | 0
32 | [7 empty] | 0
33 | [7 empty] | 0
34 | [7 empty] | 0
35 | [7 empty] | 0
36 | [7 empty] | 0
37 | [7 empty] | 0
38 | [7 empty] | 0
39 | [7 empty] | 0
40 | [7 empty] | 0
41 | [7 empty] | 0
42 | [7 empty] | 0
43 | [7 empty] | 0
44 | [7 empty] | 0
45 | [7 empty] | 0
46 | [7 empty] | 0
47 | [7 empty] | 0
48 | [7 empty] | 0
49 | [7 empty] | 0
50 | [7 empty] | 0
51 | [7 empty] | 0
52 | [7 empty] | 0
53 | [7 empty] | 0
54 | [7 empty] | 0
55 | [7 empty] | 0
56 | [7 empty] | 0
57 | [7 empty] | 0
58 | [7 empty] | 0
59 | [7 empty] | 0
60 | [7 empty] | 0
61 | [7 empty] | 0
62 | [7 empty] | 0
63 | [7 empty] | 0
64 | [7 empty] | 0
65 | [7 empty] | 0
66 | [7 empty] | 0
67 | [7 empty] | 0
68 | [7 empty] | 0
69 | [7 empty] | 0
70 | [7 empty] | 0
71 | [7 empty] | 0
72 | [7 empty] | 0
73 | [7 empty] | 0
74 | [7 empty] | 0
75 | [7 empty] | 0
Note on C4: Problem statement from the charter.
Note on E5: 1 = Low Feasibility of implementation 5 = Medium 10 = High Feasibility
Note on G5: 1=High Effort 5= Medium Effort 10= Low Effort
Note on H5: 1=Low impact 5= Medium Impact 10= High Impact This criteria is weighted by 2
Note on I5: 1=High Cost 5= Medium Cost 10= Low Cost
Note on K5: Choose whether this action will be implemented.