## Charter Instructions
Charter Guide and Instructions
Purpose
The project charter is a document that officially starts a project. It formally authorizes the existence of the project and provides a clear statement of the projects goals, scope and identifies team members for the project effort. It also serves as an agreement between all stakeholders on what needs to be accomplished.
Instructions
1. Project Leader / Green Belt will fill out the charter with the project Champion and process owner.
2. Fill in each area of the charter. Comments are available for reference for each section if needed (scroll over the red triangle to see comments). > Work Breakdown sheet is populated. Refine or adjust if you desire to add more detail. Ensure these new tasks are added to your Gantt chart. > Complete the Gantt Chart (based on your WBS tasks) with dates.
3. Prior to project kick off, ensure the Project Champion approves the charter, input the date of their approval in cell H6.
4. For any questions about the charter, contact the Organizational Effectiveness Department, in the Division of Adminstrative Affairs.

## Project Charter Template
Project Charter (Process Improvement)
Prepared by: |  |  | Date:
General Project Information
Project Name |  |  |  |  | Approvals | Date
Project Champion/ Sponsor |  |  |  |  | Champion Approval of Charter
Project Lead / Green Belt
Process Owner
Process Impacted
Expected Start Date
Expected Completion Date
Describe the Problem or Issue, Goals, and Objectives of this project
Business Case
Problem Statement
Goal Statement
Expected Benefits
Define the Project Scope and Schedule
In Scope | Start: First step of the process in question End: Last step of the process in question
Outside of Scope
Describe Project Risks, Constraints, and Assumptions
Risks
Constraints
Assumptions
Tentative Schedule |  |  | Estimated Start | Estimated Complete
Key Milestones / Phases
Form Project Team / Preliminary Review / Scoping |  |  | 2023-03-02
Finalize Project Plan / Charter / Kick Off
Define Phase
Measurement Phase
Analysis Phase
Improvement Phase
Control Phase
Project Summary Report and Close Out
Define the Project Resources
Project Team | Name | Name | Name | Name
Note on B6: The Senior Leader in the key area that will provide leadership, has the authority to sign off on the project, provide resources, clarify scope, and resolve barriers or conflicts.
Note on B7: Green Belt / Project Leader: The individual who will lead / facilitate the project from start to finish.
Note on B8: Process Owner: Individual that is accountable for the entire process. Especially important if the project spans multiple teams/work units.
Note on B9: Name of the process that will be worked on.
Note on B13: Business Case: Explain why it is important to do this project; provide justification for us to take the time and investment to do the project - eg. will it improve customer experience, meets a organizational initiative, provide financial benefit.
Note on B14: Problem Statement: A description of the problem / opportunity in clear concise, measurable terms. Do not assign blame or assume cause in the problem statement.
Note on B15: Concise statement describing the goal and success criteria. Use SMART when developing your goal statement. S: Specific M: Measurable A: Achieveable R: Relevant T: Time bound
Note on B16: What estimated benefits will be had from this project - eg. Cost reduction, increase capacity, avoid future cost, increase revenue, etc. Provide estimated values in business case and this field to strengthen case.
Note on B18: What is in scope for this project. What is the start of this process?
Note on B19: What is out of scope for this project. What is the finish or the last process step.
Note on B21: Risk to the project: An uncertain event or set of circumstances that, should it occur, will have an effect on Scope, Quality, Effort, and/or timeline.
Note on B22: Contraint: A limitation or restriction that could impact the project.
Note on B23: Assumptions made: Project factor that is considered to be true, real, or certain without proof or demonstration.
Note on B35: Add individuals who will serve as team members to the project, eg subject matter experts, etc.

## WBS
Work Breakdown Structure

## Gantt Chart Template
PROJECT NAME
Sponsoring Division/Department
| Project Activities |  |  | DURATION (Days) | ASSIGNED TO | STATUS
| START DATE | END DATE | DESCRIPTION
| 2024-06-01 | 2024-06-09 | Define 1.0 | 8
| 2024-06-02 | 2025-10-09 | Team Charter 1.1 | 487
| 2024-06-05 | 2024-07-10 | ID CCRs 1.2 | 35
| 2024-07-01 | 2024-08-10 | Stakeholder Analysis 1.3 | 39
| 2024-07-05 | 2024-08-05 | Define Tollgate | 30
| 2024-08-05 | 2024-08-22 | Measure 2.0 | 17
| 2024-08-05 | 2024-08-15 | SIPOC 2.1 | 10
| 2024-08-08 | 2024-08-16 | Current State Map 2.2 | 8
| 2024-08-09 | 2024-08-17 | Baseline Performance 2.3 | 8
| 2024-08-10 | 2024-08-18 | Measure Tollgate | 8
| 2024-08-11 | 2024-08-19 | Analyze 3.0 | 8
| 2024-08-12 | 2024-08-20 | Process Analysis 3.1 | 8
| 2024-08-13 | 2024-08-21 | ID Waste, Data elements 3.2 | 8
| 2024-08-14 | 2024-08-23 | ID Root Causes 3.3 | 9
| 2024-08-15 | 2024-09-01 | Analyze Tollgate | 16
| 2024-08-16 | 2024-09-10 | Improve 4.0 | 24
| 2024-08-17 | 2024-09-25 | Develop Solutions 4.1 | 38
` | 2024-09-10 | 2024-09-18 | Pilot Changes 4.2 | 8
| 2024-08-11 | 2024-09-19 | Confirm results / Implement 4.3 | 38
| 2024-08-12 | 2024-09-20 | Improve Tollgate | 38
| 2024-08-13 | 2024-10-21 | Control 5.0 | 68
| 2024-08-14 | 2024-10-23 | Calculate new process capability 5.1 | 69
| 2024-08-15 | 2024-10-01 | Develop training / SOPs 5.2 | 46 |  |  | ` | ` | ` | ` | `
| 2024-08-16 | 2024-10-10 | Control Plan 5.3 | 54
| 2024-08-17 | 2024-10-25 | Celebration / Transition 5.4 | 68
| 2024-08-14 | 2024-10-26 | Control Tollgate / Close 5.5 | 72
| 2024-08-15 | 2024-10-02 | TASK27 | 47
| 2024-08-16 | 2024-10-03 | TASK28 | 47
| 2024-08-17 | 2024-10-04 | TASK29 | 47
| 2024-08-14 | 2024-10-05 | TASK30 | 51
| 2024-08-15 | 2024-10-06 | TASK31 | 51
| 2024-08-16 | 2024-10-07 | TASK32 | 51
| 2024-08-17 | 2024-10-08 | TASK33 | 51
| 2024-08-14 | 2024-10-09 | TASK34 | 55
| 2024-08-15 | 2024-10-11 | TASK35 | 56
| 2024-08-16 | 2024-10-12 | TASK36 | 56
| 2024-08-17 | 2024-10-13 | TASK37 | 56
| 2024-08-14 | 2024-10-14 | TASK38 | 60
| 2024-08-15 | 2024-10-15 | TASK39 | 60
| 2024-08-16 | 2024-10-16 | TASK40 | 60
| 2024-08-17 | 2024-10-27 | TASK41 | 70
| 2024-08-16 | 2024-10-18 | TASK42 | 62
| 2024-08-17 | 2024-10-19 | TASK43 | 62
ATTENTION! You have project tasks that are overdue. Please adjust your project schedule and timeline to account for delays.