## Checklist by Date
Status | Start Date | End Date | Process Supported | Task Description | Lead Entity | Secondary Entity | Predecessors
| AY1: After add/drop | AY1: Sept 30 | Administrative | Send early notification email to Dept Chair, PAL; Cc College Dean, College Assessment Liaison (CAL), Faculty Fellow | OAPR | N/A
| AY1: Dec 1 | AY1: Feb 1 | Administrative | Send official launch letter to Department/Degree Program(s); Cc to College Dean | OAPR | N/A
| AY1: Feb 1 | AY1: April 15 | Administrative | Launch meeting with Department and/or Program Chair, and Self-Study Author(s) | OAPR | Department/Program
| AY1: Feb 1 | AY1: June 30 | Self-Study | Provide self-study template with institutional data | OAPR | N/A
| AY1: Feb 1 | AY1: May 25 | Self-Study | Identify program point of contact, writer(s) and self-study team | Department/Program | N/A
| AY1: Feb 15 | AY2: Aug 25 | External Review | Identify potential external reviewers; send CVs to the Office of Assessment and Program Review | Department/Program | N/A
| AY1: May 20 | AY2: Sept 30 | External Review | Work with college deans to finalize external reviewers | OAPR | College Dean
| AY1: May 20 | AY2: Sept 30 | External Review | Confirm ongoing interest of external reviewers | OAPR | N/A
| AY1: May 2 | AY2: Nov 15 | Self-Study | Refine and administer faculty and alumni survey (optional) | OAPR | Department/Program
| AY1: May 22 | AY2: Dec 7 | Self-Study | Write the self-study (initial draft) | Department/Program | N/A
| AY2: Aug 19 | AY2: Dec 15 | External Review | Finalize external review dates | OAPR | N/A
| AY2: Sept 15 | AY2: Nov 15 | Administrative | Identify lead PRC faculty for program assignments | PRC | N/A
| AY2: Oct 1 | AY2: Oct 31 | External Review | Send an official letter of invitation to external reviewers | OAPR | N/A
| AY2: Nov 1 | AY2: Dec 7 | Self-Study | Submit the self-study (initial draft) to the Office of Assessment and Program Review | Department/Program | N/A
| AY2: Dec 8 | AY2: Jan 10 | Self-Study | Review self-study (initial draft) and provide feedback - PRC review | PRC | N/A
| AY2: Dec 8 | AY2: Jan 16 | Self-Study | Review self-study (initial draft) and provide feedback - OAPR review | OAPR | N/A
| AY2: Dec 8 | AY2: Jan 16 | Self-Study | Provide program review self-study (initial draft) to Deans | OAPR | N/A
| AY2: Jan 16 | AY2: Feb 28 | Self-Study | Incorporate program review self-study feedback; send final version (Word doc) to Office of Assessment and Program Review for final check | Department/Program | N/A
| AY2: Feb 1 | AY2: Feb 28 | External Review | Set up and conduct teleconference to kickoff - External reviewers, dept chair, OAPR | OAPR | N/A
| AY2: Jan 20 | AY2: Mar 15 | External Review | Make hotel researvations for external review | Department/Program | N/A
| AY2: Jan 20 | AY2: Mar 15 | External Review | Schedule travel | External Reviewers | N/A
| AY2: Feb 1 | AY2: March 31 | Self-Study | Send the self-study (finalized PDF) to college dean | OAPR | N/A
| AY2: Feb 1 | AY2: March 31 | External Review | Send the self-study (finalized PDF) and summary sheet to external reviewers | OAPR | N/A
| AY2: Feb 1 | AY2: March 31 | External Review | Establish external review schedule and agenda | Department/Program | N/A | After final self-study is completed
| AY2: Feb 1 | AY2: March 31 | External Review | Review final self-study | External Reviewers | N/A
| AY2: Feb 15 | AY2: May 25 | Administrative | Identify membership of CPP Program Review Committee for following year | Academic Senate | OAPR
| AY2: Feb 1 | AY2: Apr 30 | Internal Review | Internal review - Lead and secondary PRC faculty reviewer meet with the program for 1 hour | PRC | Department/Program
| AY2: Mar 1 | AY2: May 24 | Internal Review | Lead faculty completes internal report - Submit to Office of Assessment and Program Review (30 days from visit) | PRC | N/A
| AY2: Mar 1 | AY2: Apr 30 | External Review | Site visit | External Reviewers | Department/Program
| AY2: Apr 1 | AY2: May 24 | External Review | External Reviewers complete report (30 days from visit) - Submit to Office of Assessment and Program Review | External Reviewers | N/A
| AY2: May 1 | AY2: May 24 | External Review | Forward external and internal review reports to department and Dean - outline next steps | OAPR | Department/Program
| AY2: May 1 | AY2: May 24 | External Review | Pay externdal reviewer honorariums (Office of Academic Programs) | OAPR | N/A
| AY2: May 1 | AY2: May 24 | External Review | Pay travel costs for external reviewers | Department/Program | N/A
| AY2: Jun 1 | AY3: Aug 1 | Administrative | Summarize all program review findings | PRC | OAPR
| AY3: Sept 1 | AY3: Nov 30 | MOU | Develop program response and action plan, discuss with T/TT faculty | Department/Program | N/A
| AY3: Sept 30 | AY3: Dec 15 | MOU | Set up dean-department chair meeting to discuss response and action plan | Department/Program | College Dean
| AY3: Oct 1 | AY3: Dec 22 | MOU | Modify action plan - as needed | Department/Program | N/A
| AY3: Oct 1 | AY3: Dec 22 | MOU | Write dean's response; signed final response and action plan to Office of Assessment and Program Review | College Dean | Department/Program
| AY3: Oct 1 | AY3: Dec 22 | Program Review | Notifies the Chancellor’s Office of the Program Review Completion | OAPR | N/A
| AY3: Jan 1 | AY3: Marc 15 | Administrative | Submit Program Review to Academic Senate | OAPR | N/A
| AY3: Nov 1 | AY3: Dec 22 | MOU | Set up Provost-Dean-Dept Chair MOU discussion and meeting | OAPR | N/A
| AY3: Jan 10 | AY3: Feb 28 | MOU | Take notes at MOU meeting | OAPR | N/A
| AY3: Jan 10 | AY3: Feb 28 | MOU | Prepare final MOU to be signed by Provost, Dean and Dept Chair | OAPR | N/A
| AY3: Jan 10 | AY3: Feb 28 | MOU | Sign MOU - Provost | Provost | OAPR
| AY3: Jan 10 | AY3: Feb 28 | MOU | Sign MOU - College Dean | College Dean | OAPR
| AY3: Jan 10 | AY3: Feb 28 | MOU | Sign MOU - Department Chair | Department/Program | OAPR